## Slide 1: Proces for NIR-formidlingsproject
Experiment/ research phase
Design of School experiment
Presentation
Test of detector and substrate materials
What is doable?
Scope
Investigate target group (level of understanding, what do they know)
Didactic goals
‘Dramaturgy’ of the experiment
The Driving question
Narrative and storytelling around experiment
Product deliveries 1:
- PP, talking points, worksheets for experiment, worksheet for prep and post-work for schools
Test
Test of school experiment with a school class
Dec 23
Feb 24
Notes: ##-AccessibilityAssistant: Skip layout check-##

## Slide 2
Delivery of final product
Dissimination to other formidlere
Narrative and storytelling around experiment
Finalization of product deliveries 1
Product deliveries 2:
- Material list
- Shopping list
- Kit list
Example
March 24
Notes: ##-AccessibilityAssistant: Skip layout check-##